## Functional Bugs
| Description | Status | Assigned to | Planned Fixed Date | Last Status Update Date | Team Remarks | Closing Remarks by Zeeshan
1 | Multiple copies of artifacts during remove and restore in the models Tab. | Assigned | Ahsan |  | 2022-02-21 | It has been done for model only, catalog and matrix work was not done before so, he's working on it.
2 | Multiple repository folders separate for models and recycle bin in the models tab. | Assigned | Ali/Ahsan |  | 2022-02-06
2 | Translate is not working properly. | Fixed | Ahsan |  | 2022-02-05 | It is working perfectly on our local host. For online there might be some internet issue.
3 | Objects palette is not showing in Arabic. | In Progress | Ahsan |  | 2022-02-05 | It is working perfectly for Archimate Metamodel. Translation for eaxee metamodel is remaining.
4 | Exporting empty model neither exports nor gives any message. It must show a message to the user stating that empty model can't be exported. | Assigned | Ali |  | 2022-02-05
5 | Loading delay causing distortion of interface. | Fixed | Ali/Ahsan |  | 2022-02-28 | It is fixed now.
6 | Filter option is still moving to next line when the pane is narrowed. | Fixed | Ali/Ahsan |  | 2022-02-05 | It is fixed now.
7 | Models tab shows two Lambda Theta folders. | Fixed | Ali/Ahsan |  | 2022-02-21 | Issue resolve on local, it will update on live soon.
8 | Recycle bin icon is not the same in Objects and Models tab. | Fixed | Ali/Ahsan |  | 2022-02-21 | Issue resolve on local, it will update on live soon.
9 | Object save operation is slow. | Fixed | Ali/Ahsan |  | 2022-02-05 | Issue resolve on local, it will update on live soon.
10 | The objects tree collapse operation halts/stops working. | Fixed | Ali/Ahsan |  | 2022-02-05
11 | Recycle bin must be the last folder in the same tree and not in a different tree. | Assigned | Ali/Ahsan |  | 2022-02-05 | It's a new feature. Will work on this later.
12 | Recycle bin folder getting adjacent with objects folder. | Assigned | Ali/Ahsan |  | 2022-02-05
13 | Objects and Models panels blink and adjust multiple times during loading. | Fixed | Ali/Ahsan |  | 2022-02-05
14 | Playing with renaming and saving objects stops tree from responding. It needs relogin to bring it to normal operation. | Fixed | Ali/Ahsan |  | 2022-02-05 | Issue resolve on local, it will update on live soon.
15 | Clicking Ctrl+Save open file save dialog box trying to save EAXEE.html. | Closed |  |  | 2022-02-05 | It is default function. It can't be change. | It is closed based on justification provided by the team.
16 | Relationship dialog box in not closing after showing error that 'Another User has ...'. | In Progress | Ali/Ahsan |  | 2022-02-05
17 | Self relationship is not allowed. Currently, it's allowing and this is not acceptable. | Fixed | Ali |  | 2022-02-05
18 | Simply changing the attributes and saving gives 'Another user has ...' error. And saving is not done. It looks like issue with the multiple changes of attributes. This must be corrected. | Assigned | Ali/Ahsan |  | 2022-02-05
19 | Repeated saving after attributes changes of the same object gives 'Another User has ...' error. | Assigned | Ali/Ahsan |  | 2022-02-05
20 | No Folder for GANTT Chart. | Fixed | Shoaib |  | 2022-02-09 | Gantt Chart is replaced by Roadmap
21 | Red colored text at the bottom letf appears with web address and other parameters. | Assigned |  |  | 2022-02-05
22 | Multiple scroll bars in the models upon creating diagrams. | Assigned | Ali/Ahsan |  | 2022-02-05
23 | Alignment and placing of Object/Models buttons etc. between languages. | Fixed | Ahsan |  | 2022-02-05 | updated on live
24 | Object and Models tabs switch position between languages. | Assigned | Ali/Ahsan |  | 2022-02-05
25 | The EAXEE meta-model does not have Relationship Connectors. Therefore, the folder for Relationship Connector must not appear in the Objects tab for any meta-model that doesn't have relationship connector. | Assigned | Ali/Ahsan |  | 2022-02-06
27 | Relationship objects are not appearing in the Relationship tree. | Fixed | Ali |  | 2022-02-22 | Its already working fine. Will update on live soon.
28 | Import doesn’t work properly. | Fixed | Shoaib |  | 2022-03-01 | Issue resolve on local, it will update on live soon.
29 | Log out doesn’t work after import. | Fixed | Ahsan |  | 2022-03-01 | Issue resolve on local, it will update on live soon.
30 | All attributes are not export correctly. For Example: Introduction Method and Introduction Method Note. | In Progress | Shoaib |  | 2022-02-24 | Issue resolve on local, it will update on live soon.
31 | FromExcel page is not redirecting to login page after logout. | Fixed | Shoaib |  | 2022-02-09 | It is resolve on local but remain to change on live.
32 | Register New Architect page is not redirecting to login page after logout. | Fixed | Shoaib |  | 2022-02-09 | It is resolve on local but remain to change on live.
33 | createRepository page is not redirecting to login page after logout. | Fixed | Shoaib |  | 2022-02-09 | It is resolve on local but remain to change on live.
34 | modal is not closing after clicking close button | Fixed | Ahsan |  | 2022-02-10 | It is resolve and updated on live.
35 | Matrix feature is not working properly. The element selection drop-down list is not showing all elements. Also, sometimes there is nothing shown in a drop-down list. Moreover, the drop-down list after selection of an element gets disabled and doesn’t allow to change the selected element. | Fixed | Sohail |  | 2022-02-16 | Rest of the elements shown according to selected matrix.
36 | Mutiple copies of the same matrix appear in the history box. | Fixed | Sohail |  | 2022-02-16 | Issue resolve on local, it will update on live soon.
37 | Matrix is not updated once created. For example, the name of objects included in a matrix don't update after renaming. Please note that the matrix should be updated based on renaming of objects or change of relationships among them. It should remain dynamic and should be updated automatically based on changes in the included objects. The same principle must be applied on Catalogs. | Assigned | Arbab |  | 2022-02-21 | it is not a bug it’s a new feature. Because when a matrix is created it is saved in xml format and stored in database and then next time when we clicked on saved matrix it is retrieve from saved xml so that’s why it will take time | If this one is important so then we can work on it
38 | The name of matrix in the title model bar is not showing correctly. It shows two different names for the same matrix. | Assigned | Arbab |  | 2022-02-13
39 | The same matrix is displayed multiple times in the model canvas. | Fixed | Arbab |  | 2022-02-21 | Issue resolve on local, it will update on live soon.
40 | Matrix selection is not showing correct list of items. Sometimes it doesn’t show even anything. | Assigned | Arbab |  | 2022-02-13
41 | matrix Check marks should be center align | Fixed | Arbab |  | 2022-02-21 | Updated on local. Need to update on live.
42 | refresh button on matrix page to refresh matrix at instant | Assigned | Arbab |  | 2022-02-21 | it is not a bug it’s a new feature. Because when a matrix is created it is saved in xml format and stored in database and then next time when we clicked on saved matrix it is retrieve from saved xml so that’s why it will take time
43 | Does not create matrix. | Fixed | Arbab |  | 2022-02-22 | Issue resolve on local, it will update on live soon.
44 | Export file doesnot contain column values. | Fixed | Shoaib |  | 2022-02-13 | Updated on local. Need to update on live.
45 | The drop down menu for objects relationship on the drawing canvas is not showing correct possible relationships. In fact, it's showing irrelevant text 'No'. See Screenshot called 'Irrelevant Text'. | Fixed | Ali |  | 2022-02-22 | Issue resolve on local, it will update on live soon.
46 | Existing objects from the Objects Tree are not appearing on the drawing canvas upon drag-and-drop. | Fixed | Ali |  | 2022-03-05
47 | Some objects on the drawing canvas don't show element symbols on the rectangular box. See screenshot called 'Missing Symbols'. | Assigned | Ali
48 | Trying creating objects of some elements such as 'Organization Unit' upon creation on canvas don't create objects in the Objects Tree. Only shapes are placed on the canvas with no actual object created. See screenshots called 'No Actual Objects Created 1 and No Actual Objects Created 2'. | Assigned | Ali/Ahsan
49 | The object's form dialog box opened from the drawing canvas can not be closed. The 'x' button doesn't work. | Assigned | Ali/Ahsan
50 | It appears that the time attributes of the objects are storing values automatically such as 'Average Execution Time' attribute of 'Business Process' objects. See screenshots 'Automatic Time Capture 1', 'Automatic Time Capture 2' and 'Automatic Time Capture 3'. | Assigned | Ali/Ahsan
51 | Object Tree hierarchi in Arabic is not showing all the translated text. Some text still appears in English. Moreover, a weird string with date and time is also attached to one of the folder's text in the tree. See screenshot called 'Arabic Text Issues'. | Assigned | Ali/Ahsan
52 | Drawing canvas in Arabic is not fitted properly in the computer screen. It appears to be cut from the left side. Moreover, the symbols palette is still missing. See screenshot called 'Arabic Canvas'. | Assigned | Ali/Ahsan
53 | Export through Excel crashes the Software. See screenshot called 'Export Crash'. | Fixed | Shoaib |  | 2022-02-24 | issue resolve on local. Will update on live soon.
54 | Charts can not be generated on the Organization Portal because 'Generate' button is disabled even after selecting all the dialog box parameters. See screenshot called 'No Chart Generate'. | Assigned | Ahsan
55 | Catalog is showing date values in many relationship attributes for all objects. See screenshots called 'Catalog dates in relationship 1' and 'Catalog dates in relationship 2'. Also, look at 'Applications Catalog' Excel file exported from the catalog. | Assigned | Arbab
56 | The tabular structure of the created catalog breaks after some columns. See screenshot called 'Catalog Tabular Display Breaks'. | Assigned | Arbab
57 | A weird data table initialization error is shown upon creating a catalog. See screenshot called 'Catalog Data Table Issue'. | Assigned | Arbab
58 | Relationship is not creating in canvas among objects | Fixed | Ali |  | 2022-02-21 | The issue has been resolve on local. Remain to update on live.
59 | The matrix is putting check-marks in the cells only for forward relations. The check marks must be put for both directions of selected relationship. For example, if 'Composition' relationship is selected for a matrix between 'Application Component' and 'Business Process' then it must put check-marks for both 'Composed of' and 'Part of' directions. See the screenshot called 'Matrix Direction'. | Assigned | Arbab |  | 2022-02-21
60 | Pi chart doesn't show correctly. | Fixed | Ahsan |  | 2022-02-25 | The issue has been resolve on local. Remain to update on live.
61 | Metamodeler add in modules. | Assigned | Ali |  | 2022-03-04
62 | MODULES -> EAXEE SUITE / SPECTRUM | Assigned | Ali/Ahsan |  | 2022-03-04
63 | Show Admin Module in Administration just only UI and show work for concurrent users. | Assigned | Ali |  | 2022-03-04
64 | On pool remove, license will be free. | Assigned | Ali |  | 2022-03-04
65 | EAXEE icons error | Assigned | Arbab |  | 2022-03-04
66 | Set table row height same for all. | Fixed | Ahsan |  | 2022-03-26
67 | On canvas delete by default select on icon (paletter) | Assigned | Ali/Ahsan |  | 2022-03-04
68 | In the left bottom of the box show its element symbol (After demo) | Assigned | Arbab |  | 2022-03-04
69 | Hand on the canvas (After Demo) | Assigned | Arbab |  | 2022-03-04
70 | Fixed canvas area | Assigned | Ali/Ahsan |  | 2022-03-04
71 | Remove relationship in the form if it is deleted from canvas | Assigned | Ali |  | 2022-03-04
72 | Download matrix on the navbar | Assigned | Ali/Ahsan |  | 2022-03-04
73 | Add multiple tabs on charts | Assigned | Ahsan |  | 2022-03-04
74 | Right align text | Fixed | Ahsan |  | 2022-03-12
75 | Background color on RTL view | Fixed | Ahsan |  | 2022-03-04
76 | User profile page on explorer page | Assigned | Ali/Ahsan |  | 2022-03-04
77 | Home, Arabic and history tab | Fixed | Ahsan |  | 2022-03-04
78 | sign out remove from user profile | Assigned | Ali/Ahsan |  | 2022-03-04
79 | tooltips and icon | Assigned | Arbab |  | 2022-03-04
80 | user profile page on explorer page | Assigned | Ali/Ahsan |  | 2022-03-04
81 | add + circle shape | Fixed | Ahsan |  | 2022-03-12
82 | center align | Assigned | Shoaib |  | 2022-03-04
83 | legend align on pie | Fixed | Ahsan |  | 2022-03-12
84 | try valid chart alert option | Fixed | Ahsan |  | 2022-03-12
85 | add page on charts | Assigned | Ahsan |  | 2022-03-04
86 | page title fixed for charts | Assigned | Ahsan |  | 2022-03-04
87 | import / export button style | Assigned | Shoaib |  | 2022-03-04
88 | Save option for charts container | Fixed | Ahsan |  | 2022-03-12
89 | same value is not allowed for more than one dropdown | Assigned | Shoaib |  | 2022-03-04
90 | it shows all possible for legends | Assigned | Shoaib |  | 2022-03-04
91 | if finish date at first or start date at second, it should not generate roadmap | Assigned | Shoaib |  | 2022-03-04
92 | history tab alignment | Assigned | Ali/Ahsan |  | 2022-03-04
93 | title is on centre position | Assigned | Ali/Ahsan |  | 2022-03-04
94 | relationship row max "4" min row "1" | Assigned |  |  | 2022-03-04
95 | check max limit of relationship | Assigned | Ali |  | 2022-03-04
89 | Delete also word for one chart | Assigned | Ahsan |  | 2022-03-04
90 | Change name from Other #SAT Mar 12 12:49 to Other | Assigned | Ahsan |  | 2022-03-04
91 | Values in textfield should translate at run time
Additional Features
1 | General view |  |  |  | 2022-03-14
2 | Use customized view: 1) Created by a user. 2) show only attributes or everything for customized user |  |  |  | 2022-03-14
3 | Two windows one for general and one for the user defined view. |  |  |  | 2022-03-14
4 | Onclick hide relationship connections from the canvas. |  |  |  | 2022-03-14
5 | Similar view but customized for a user. |  |  |  | 2022-03-14
6 | Show only objects onclick remove connections. |  |  |  | 2022-03-14
7 | Add button hide/unhide (Demo) |  |  |  | 2022-03-14
8 | Display as icon |  |  |  | 2022-03-14
9 | Hover color top |  |  |  | 2022-03-14
10 | Palette hide |  |  |  | 2022-03-14
11 | Highlight click object |  |  |  | 2022-03-14
12 | Onchange refresh change text |  |  |  | 2022-03-14
13 | check all translated text |  |  |  | 2022-03-14
14 | Apply check on IMPEX |  |  |  | 2022-03-14
15 | Check the date which comes from the database |  |  |  | 2022-03-14
16 | check full mirror image for RTL view. |  |  |  | 2022-03-14
17 | Element -> Select object. Show only those relationship whose relationship exist. |  |  |  | 2022-03-14
18 | Add duplicate repository check on IMPEX |  |  |  | 2022-03-14
19 | Relationship object and element Object should not be duplicate. |  |  |  | 2022-03-14
20 | Relationship check on updated values. |  |  |  | 2022-03-14
21 | Save as option on model |  |  |  | 2022-03-14
22 | Add title option in chart |  |  |  | 2022-03-14
91 | Download option in Pie chart | Fixed | Ahsan |  | 2022-03-04

## Security Bugs
# | Description | Status | Assigned to | Planned Fixed Date | Last Status Update Date | Team Remerks | Closing Remarks by Zeeshan
1 | Does not allow multiple user access on FromExcel page | Fixed | Shoaib | 2022-02-10 | 2022-02-12 | I've done this manually and it's working fine. It allow mulptiple user to access manually.
2 | Session timeout work has not done. | Fixed | Ali/Ahsan | 2022-02-10 | 2022-02-11 | Session timout work has been done on local. It need to update on live.
3 | Test SQL-injection on Eaxee website. | Fixed | Shoaib | 2021-02-15
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31